## Sheet1
| Question |  | Response
1 | Will full plans be available? | 1 | The full plans are on the City's website with the RFP.
2 | Where are the appendices noted in the index? | 2 | There are no appendices other than building plans, please disregard
3 | Is the 2nd floor sub floor intended to be plywood? | 3 | 3/4" Plywood or equal
4 | Is a steel column or stud pack required for the 2nd floor framing plan? | 4 | See revised sheets A2 & S1
5 | Is this a public work to be held at 5% retainage fee per GA law? | 5 | Yes, we will follow ACT 781
6 | Will the building be occupied during construction? | 6 | The existing City Hall structure will remain open and operational.
7 | No drains or scuppers are shown; how will water be removed from the roof? | 7 | See revised sheets A4, A5, & A7
8 | Will a fire suppression system be required? | 8 | No
8b | Is the existing building sprinkled and will the addition be tied in? | 8b | N/A
9 | Regarding Sec. 01250 - please confirm there is no Fire Station. | 9 | There is no fire station associated with this project.
10 | Bid from article 5 notes sectional doors, there are none on drawings: please clarify. | 10 | See revised documents
11 | How will walls tie in to the existing building? (Ref: Sheet A2 1st floor) | 11 | See revised cover sheet
12 | Please clarify the total building area | 12 | See revised sheet A6
13 | What is the material for the column wrap | 13 | See Section 1/S5
14 | What are the manufaturer/materials/warranty for the Arch Shingles? | 14 | See revised sheets A4 & A5. Shingle type and color to match existing.
15 | What is the material/size/color of brick or material allowance? | 15 | Brick veneer shall match existing.
16 | What is the manufacturer information for the roof hatch? | 16 | See revised sheet A7
17 | Is the owner providing and installing the the TV mount? (Sheets A9 & A10) | 17 | Owner to select, GC to install
18 | Please provide information on doors/frames/hardware | 18 | See revised sheet A11
19 | Will the owner consider powder-coated aluminum for the project? | 19 | Yes
20 | Is the owner paying permitting and inspections costs. | 20 | Permitting and inspections are required, fees to be waived.
21 | Is there product/manufaturer information for finish material (sheet A11)? | 21 | Contractor to provide allowance within normal range of type material listed on Sheet A11.