## Sheet1
PRECONSTRUCTION REQUEST FOR INFORMATION
Project Name: Anchor Park Phase 2
Location: Port Wentworth, GA
Status | Questions | Assigned Discipline/Firm | Response | DWG | SPEC
Open | It came across my desk because there's apparently a netting system called for in the scope of work, and I'm hoping to provide pricing on it. However, the plans appear to be incomplete, as I don't see any drawings or details to show where it will be going. Do you have any additional information about this netting system? | TH | Please see sheet C1.2 for the location of Jaypro Sports Multi-Sport Backstop System and sheet C3.30 for the accompanying detail.
Open | In the request for proposal "Description of Work" section, it mentions that Bleacher structures are prescribed to be installed. We do see that the plans show bleachers and I have attached them to this email. However, we do not have a specification section that pertains to Bleacher structures. | JLG | See attached specification section 13 3416 – ALL ALUMINUM FRAMED BLEACHER
Open | 1. Bid Documents (01150-3) and Notice to Proceed (01400-1) states Substantial Completion Date of 180 days, while the Agreement (01350-1) and Bid Form (Article 6.01 Time of Completion, 01250-4) states 365 days after Notice to Proceed. Please confirm that the 365 days is correct as the 180 days in unobtainable for this work. | City/TH/JLG | 245 calendar days (8 months) for substantial completion and 305 dys for final completion. Civil Sections 00 41 43, 00 80 00,
Open | Civil plan E1.0 states to refer to Musco Drawings (typ.) for details on the Sports Lighting but no schedule for those fixtures. Are these to be ‘By Owner’ or will more information be provided? | TH | MUSCO preliminary drawings attached. Contractor shall submit final MUSCO design for Owner and Engineer review prior to ordering materials.
Open | Sheet E.01 refers to spec section 26 56 68 which does not appear to be included in either of the specifications. Please advise | TH | Please see attached, 'Site Electric Specifications' for 'Section 26 56 58 - Exterior Athletic Lighting' for the missing specification.
Open | Which Bid Form needs to be submitted? Bidding Documents by City of Port Wentworth or T&H’s Bid Form? | TH | Section 00 41 43 (TH Bid form) must be completed and submitted with the bid submittal. The quantities and unit prices shall equal the contractor lump sum bid for the project. Unit costs will be used for potential field consultation change orders. The City RFP must include the number calculated from Section 00 41 42 for the Civil portion. The overall contract will be a lump sum contract.
Open | Can T&H’s Bid Form breakdown (Sheets 1-4) be submitted within 24 hours after the Bid Date? | TH | No. The bid form breakdown sheets must be submitted with the bid by the bid due date.
Open | Will the City be waiving all permits and fees for the Project? | City | Yes, all permit fees will be waived, permits are still required to be submitted through the proper office
Open | 1. It appears the Geotechnical Report under Subsurface Investigation (02 30 00) was not performed at the Phase 2 location or layout. Please confirm. | TH | Additional geotechnical reports have been provided for Bidder reference.
Open | Please confirm that the Canopy above the Bleachers is ‘By Others’ as shown on 4C/A203. If not, please provide more information. | JLG | The fabric shade canopy is included in the project but does not have to be included in the aluminum bleacher contractors. See specification section 13 3100 Fabric Structures for more information on fabric shade and structure. See revised sheet A203.
Open | The specifications do not match the bleacher drawings. Section 12000 are for “fixed upholstered” seating. Section 13000 is for “fabric shade” only, no mention of bleachers. The drawing is for aluminum seating. Can we get clarification on what is actually bidding as far as the outdoor seating. | JLG | Aluminum seating and a fabric shade are included in the project. See attached specification section 13 3416 – ALL ALUMINUM FRAMED BLEACHER and specification section 13 3100 Fabric Structures.
Open | No detail pertaining to the press box roof is given. Please provide. | JLG | Roof to be designed by Bleacher Supplier. See attached specification section 13 3417 – PRESS BOX
Open | Does alternate 6A-1 & 6B-1 apply to entirety of parapet wall system? Please confirm | JLG | Alternate 6A-1 and 6B-1 are applicable for the full parapet wall system. The differences being the material used to frame the parapet (CMU in 6/S400, structural steel channels in 6A-1, and CFS in 6B-2).
Open | No details for round-a-about on Sheet C1.4. Please provide. | TH | Please review construction plans. The Roundabouts not included in scope of work. Please note phase line on Sheet C1.4 which demarcates the limits of Phase 2 construction.
Open | No manufacturer/size/color/etc. are selected for the pervious pavers. Please provide. | TH | Please see sheet C3.31 for permeable detail and note to contractor to coordinate the size, color and specifications with the owner.
Open | No details or specification section for fencing. Please provide. | TH | Please note on Sheet C1.2, call-outs for 42" High Black Vinyl Coated Chain Link Fence state " prior to the commencement of construction, contractor shall supply owner with specification drawings and manufacturer's details for proposed fencing, gates and all connecting appurtenances." Base specifications have been included in this addendum.
Open | Canopy at the front entrance is discontinued from CR Laurance (spec'd). Please provide alternate | JLG | Remove specification section 10 7300 - ALUMINUM TRELLIS. See attached specification section 10 7113.43 – FIXED SUN SCREENS.
Open | Subcontract proposals are due on a holiday shortened week and our proposals being due on the Monday after a holiday week is anticipated to diminish bidder response. Can the bid day be extended to September 16? | City | Bids will be extended to September 8th, 2025
Open | The cover page for Site Development Plans show an E1.1 but I do not see that sheet on the drawings. Please provide | TH | Sheet E1.1 was eliminated. The cover sheet has been revised.
Open | There are two C3.13 sheets and no C3.23. I assume one is supposed to be C3.23. Can you please confirm and update the incorrect sheet? | TH | Typo, the sheet numbers have been revised.
Open | Pavement Legend calls for Heavy Duty Vehicular Asphalt to have a 6" GAB but the detail on Sheet C3.28 says an 8" GAB. Which is correct? | TH | Please defer to detail. Pavement legend has been amended to reflect 8" GAB for heavy duty vehicular asphalt section pursuant to geotechnical recommendations.
Open | Can you provide a detail for the black chain link fence and gates? | TH | Please note on Sheet C1.2, call-outs for 42" High Black Vinyl Coated Chain Link Fence state " prior to the commencement of construction, contractor shall supply owner with specification drawings and manufacturer's details for proposed fencing, gates and all connecting appurtenances." Base specifications have been included in this addendum.
Open | Do you intend to provide specifications for the fence, gates, and backstop system? | TH | Please note on Sheet C1.2, call-outs for 42" High Black Vinyl Coated Chain Link Fence state " prior to the commencement of construction, contractor shall supply owner with specification drawings and manufacturer's details for proposed fencing, gates and all connecting appurtenances." Base specifications have been included in this addendum.
Open | Spec Section 32 11 23 is applicable for Asphalt Paving. Is this spec the same for Concrete Paving? | TH | Concrete paving shall be in accordance with the recommendation for Heavy Duty Concrete Pavement, as set forth in the Subsurface Explorations and Geotechnical Evaluations for the Port Wentworth Recreation Complex, dated June 6, 2023, as prepared by GHD. This reports is attached to this Addendum.
Open | Spec Section 32 11 26 -Asphaltic Base Courses was provided but is not shown on the drawings. Is it required? | TH | Included I the event there was an alternate pavement section pursuant to the geotechnical recommendations. Please disregard.
Open | Can you provide a detail for the 8" Graded Aggregate Base in the Pavement Legend? | TH | Please see sheet C3.31 for the addition of 6" graded aggregate base section (overflow parking area). Please also note that 8" GAB has been amended to 6" GAB for the overflow parking area.
Open | Field Lighting Feeder Schedule on Sheet E1.0 mentions lighting for a playground. Is the playground in our scope? | City | No, playground is not in this scope
Open | Please provide a detail for Grate Inlets. | TH | Pease see sheet C3.31 for the addition of detail SD-8, grate inlet detail.
Open | Sheet C2.8 has a detail for Reduced Pressure Detector for Fire System. I do not see where fire suppression is required on this project. Please confirm if detail is required. | TH | Reduced pressure detector for fire system has been struck from Sheet C2.8. Please see sheet C2.10 for the addition of detail W-04, RPZ device for domestic system.
Open | For the 6' Chain Link Double Swing Gate, the drawings and Bid Form say there are 12 total but I only see 4 pair (8 total). Please confirm the correct quantity. | TH | Please note on sheet C1.2, "(12' TOTAL)" refers to the total width of the gate not the total quantity. Call outs have been revised to more accurately reflect this.
Open | The RFP and the civil spec book have two different bid forms. The Civil bid form requests unit costs. Please confirm this is a lump sum proposal and unit costs are not required. | TH | Section 00 41 43 (TH Bid form) must be completed and submitted with the bid submittal. The quantities and unit prices shall equal the contractor lump sum bid for the project. Unit costs will be used for potential field consultation change orders. The City RFP must include the number calculated from Section 00 41 42 for the Civil portion. The overall contract will be a lump sum contract.
Open | Confirm footing type at the north end of bleachers on column line BL6 and adjacent to TWF2 just north of that. | JLG | Footing types for bleacher and canopy structures will be as follows: pad footings with piers for columns apart of fabric canopy structure, thickened slabs at all load bearing elements of aluminum bleachers (locations unknown), thickened slab edge around extents of aluminum bleacher layout. Referenced unknown footing should be a thickened slab where the aluminum bleacher provider is to place a ramp.
Open | On sheet G1.1 under note 35, it states all striping in the right of way to be thermoplastic. I am assuming this would refer to only the stop bars and crosswalks. Would the crosswalks within the parking area need to be thermoplastic as well? Please clarify if the parking spaces should be thermoplastic or latex. | City/TH | ADA Parking, Crosswalks and Stop bars shall be thermoplastic striping. Regular parking spaces shall be paint markings.
Open | Will there be any centerline or edge line striping required on the perimeter road? | City/TH | Centerline and edge striping is not include in the contract.
Open | According to the landscaping drawings, all areas not receiving landscaping features are to be sodding. On the final erosion control plans it is identified as DS3 which is a seed application. Can you please clarify the grassing requirements? | City/TH | Areas to be sodded include the entire area outside the field fencing to the edge of roadways and parking bays around the perimeter of the core field location. The fields shall be sodded with TifTuf Bermuda as shown on the plans. All other areas shall seeded with permanent grass seed for final stabilization.
Open | On sheet C3.28, it shows a detail for a Bio-Retention area, however we have not been able to locate this on the plan sheets. Could you please identify the location of the bio-retention area? | TH | Please see sheets C3.1, C3.4 and C3.5 for the addition of bio-retention swale call-outs.
Open | Within the specification there is a bid form with bid items with required unit rates. It states that the units installed will be measured for payment (section 01 22 00), however it also states in the specifications that these payments will be made on a lump sum basis. Can you please confirm if the pricing is based on unit cost or lump sum. | TH | Section 00 41 43 (TH Bid form) must be completed and submitted with the bid submittal. The quantities and unit prices shall equal the contractor lump sum bid for the project. Unit costs will be used for potential field consultation change orders. The City RFP must include the number calculated from Section 00 41 42 for the Civil portion. The overall contract will be a lump sum contract.
Open | On sheet G1.1 under not 28, it states that the city will make the wet tap for the services. Will this include the material and installation/setup as well for the 12x6 tapping sleeve and valve/manhole? | TH | Note has been revised. Successful bidder shall make all water line connections.
Open | There is no detail in the plans for the underdrain system install behind the curbs. Please clarify if we should use the description provided in the geo report under section 4.5.5 or provide the required detail for this installation | TH | Please see sheet C3.32, detail SD-10 6" underdrain pipe.
Open | Can the 6" underdrain be HDPE instead of PVC? If so, would it need to be single wall or double wall HDPE? | TH | Please see sheet C3.32, detail SD-10 6" underdrain pipe.
Open | On sheet C3.8, it shows in the pavement legend that the stone parking lot and drive to the future storage shed is to receive 8” GABC, however based on the bid quantities, it seems that the calculations are estimating the stone to be 6-inch GABC. Can you please clarify the thickness of the GABC in these areas? | TH | Please see sheets C1.1 and C1.5 for the addition of call-outs for 4" gravel driveway and 8" GAB overflow parking area. Please see also updated pavement legend on sheets C1.1 - C1.5 and C3.6 - C3.10. Changes include adding a hatch for 4" gravel driveway and 8" GAB.
Open | On the bid schedule, there is an item under paving and grading, item #14 labeled 4-inch Gravel Driveway. Can you please clarify where this is intended to be utilized? | TH | Please see sheet C1.1 for call-out of 4" gravel driveway.
Open | There is no pay item for striping, I am assuming this would fall under the pay item #21 under Paving and Grading (Traffic Signs)? | TH | A striping line item has been added to the bid schedule.
Open | The ACO trench drain is shown to be standalone and not up against the concrete slab. Is this correct? Typically, the trench drain would be adjacent to the concrete slab/asphalt area? | TH | Please see sheet C3.2 for relocated trench drain.
Open | Does the field installer need certifications? | TH | Americans Sports Builders Association Certified Field Builder - Natural Turf or equivalent required.
Open | Is the flat panel connecting to the collector system via hard connections or just rolling to and out letting? | TH | Hard connections
Open | Sizing of baseplates for the canopy steel | JLG | Fabric Canopy Structure is Design Build by General Contractor
Open | Column Sizing so we can plan supports around them? | JLG | Fabric Canopy Structure is Design Build by General Contractor.
Open | Anticipated sway of the columns so we can design enough space to not impact the bleachers? | JLG | Fabric Canopy Structure is Design Build by General Contractor.